## Uniphore Phase 1 (hidden)
Feature | Task | Milestone | Priority | Start Date | End Date | Status | Owner | Comments
Inference APIs | Standardize API to Rackspace product name qualifier | MVP | P0 | 2026-03-17 | 2026-03-19 | Completed | Neelava | Current name - aurora.platform9.com New name - rmpai.rackspace.com. Alternate name - - rackai.rackspace.com - rai.rackspace.com
| Publish API doc | MVP | P0 | 2026-03-19 | 2026-03-23 | In progress | Neelava
| Model Deployment API for Uniphore | MVP | P0 | TBC | TBC | Not started | TBC | Assuming that the current APIs we have are sufficient for Uniphore's use case. Need clarification and subsequent task planning if that is not the case. Pending publication of API docs
| OpenAI API compatibility for Uniphore | MVP | P0 | TBC | TBC | Not started | TBC | Assuming that only the chat completions API is the needed API here. Need clarification and subsequent task planning if that is not the case Pending publication of API docs
| Users should be able to get a token to use with the API. Should be automation friendly. | MVP | P0 | 2026-03-23 | 2026-03-27 | In progress | Neelava | Immediate implementation will be with Auth0. If not, we need to take up the Authentication work items below first.
| UI - Token management | MVP | P0 | 2026-04-01 | 2026-04-08 | Not started | Kim
Inference optimization | Utilize Uniphore's optimized NIM models | MVP | P0 | TBC | TBC | Not started | Alberto / Abhimanyu | Per Amine, in the initial phase we need to use the optimized NIM models from Uniphore and don't have to take up any extra task. Change in this assumption, will need replanning. Gemma 27 Mistral 24 GPT-OSS 20 llama 3.1 8b llama 3.2 11b visual
NIM model support | Deployment configuration to leverage NIM models or vLLM | MVP | P0 | 2026-03-16 | 2026-03-23 | In progress | Ajay
| Bootstrap product with Uniphore’s NIM models | MVP | P0 | 2026-03-24 | 2026-03-30 | Not started | Ajay | Need to understand where these models are available to use and how to integrate those model locations into the Uniphore deployment
| Model Deployment implementation for NIM models | MVP | P0 | 2026-03-16 | 2026-03-23 | In progress | Ajay
| LORA adapters working with NIM models | MVP | P0 | TBC | TBC | Not started | TBC | To be scoped
Fine Tuning | SFT - Dataset management for fine tuning (only file upload) | MVP | P0 | 2026-03-17 | 2026-04-07 | In progress | Rohit
| SFT - Customize fine tuning steps and trigger fine tuning PEFT job (LORA) to generate adapters | MVP | P0 | 2026-03-17 | 2026-03-31 | In progress | Rajendra | Running late, code not checked in yet. But PoC exists.
| SFT - Training job status reporting | MVP | P0 | 2026-04-01 | 2026-04-06 | Not started | Rajendra
| SFT - Store/Save LORA adapters for users to use with a model. | MVP | P0 | 2026-04-07 | 2026-04-16 | Not started | Rajendra
| SFT - Deploy/Undeploy LORA adapters on top of deployed base model | MVP | P0 | 2026-04-01 | 2026-04-15 | Not started | Neelava
| SFT - Multi LORA deployments | M? | P0 | TBC | TBC | Not started | Alberto / Abhimanyu | Proposal: Move this to post May deliverable
| SFT - Import/Export of LORA adapters | M? | P0 | TBC | TBC | Not started | Alberto / Abhimanyu | Proposal: Move this to post May deliverable
| SFT - Deploy on shared inference infrastructure | M? | P0 | TBC | TBC | Not started | Alberto / Abhimanyu | Proposal: Move this to post May deliverable Need clarification on what shared inference infrastructure means here.
| UI - Fine tuning workflows | M? | P0 | TBC | TBC | Not started | Kim
Model Registry | User should be able to save models to a model registry | MVP | P0 | 2026-04-01 | 2026-04-07 | Not started | Ajay | Does it have to be a self hosted option registry only? Can the first cut be with HF?
| Model Registry supported out of the box - as part of the RMPAI platform | MVP | P0 | 2026-04-08 | 2026-04-15 | Not started | Ajay
| UI - Model Registry workflows | MVP | P0 | TBC | TBC | Not started | Kim
Authentication | Remove dependency on Auth0 | M1 | P1 | TBC | TBC | Not started | TBC | To be scoped - Post May
| Use Zitadel as the authn replacement | M1 | P1 | TBC | TBC | Not started | TBC | To be scoped - Post May
| Integrate with Rackspace IDP directly, through keycloak if Zitadel doesn’t work out. | M1 | P1 | TBC | TBC | Not started | TBC | To be scoped - Post May
vn

## RACKAI - 2026 Roadmap
RackAI — Software Delivery Plan
CSP Platform Layer on real schedule (Jun 2026 – Feb 2027, per 'CSP Project Plan – FINAL') + RackAI M2 Feature Delivery (17 features · 46 man-wks) — week-start dates shown; feature bars anchored to first July week
Deliverables ▾ | [11 empty] | Jun '26 |  |  |  |  | Jul '26 |  |  |  | Aug '26 |  |  |  |  | Sep '26 |  |  |  | Oct '26 |  |  |  | Nov '26 |  |  |  |  | Dec '26 |  |  |  | Jan '27 |  |  |  | Feb '27
Workstream | Team / Owner | Task / Deliverable | M# | Jira | Assigned | Status | Pri | Effort | Start | End | Key Dependencies | 6/1 | 6/8 | 6/15 | 6/22 | 6/29 | 7/6 | 7/13 | 7/20 | 7/27 | 8/3 | 8/10 | 8/17 | 8/24 | 8/31 | 9/7 | 9/14 | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18 | 1/25 | 2/1 | 2/8 | 2/15 | 2/22
CSP PLATFORM LAYER — real schedule per 'CSP Project Plan – FINAL' (Identity · Monitoring · Metering · Auditing · Observability)
IAC | Team IAC | JWT + API-key validation, identity context headers, APIKey CRD, Gateway auth | M1 | RACKAI-204 | Erik Ljungstrom | Complete |  | 2 | 7/6 | 2026-07-17 | — (day-one foundation) | bar: Jul '26 7/6
IAC | Team IAC | PlatformRole + RoleBinding CRDs, Authorization Service, K8s informer-based RoleBinding lookup, RBAC enforcement | M2 | RACKAI-333 | Erik Ljungstrom | Complete |  | 1 | 2026-07-20 | 2026-07-24 | IAC M1 | bar: Jul '26 7/20
IAC | Team IAC | Audit Log query API, sensitive access logging, login events, APIKey lifecycle events | M3 | RACKAI-351 | Erik Ljungstrom | Complete |  | 1 | 2026-07-27 | 2026-07-31 | IAC M2 | bar: Jul '26 7/27
IAC | Team IAC | Metering/billing/quota/observability permission integration, org-level RBAC | M4 |  |  | Won't Do |  | 3 | 2026-08-03 | 2026-08-21 | IAC M3 | bar: Aug '26 8/3
Platform | Team Platform | Prometheus Operator, DCGM, node-exporter, AlertManager, Grafana, GPU/cluster dashboards | M1 | RACKAI-353 | Abhimanyu Sharma | In Progress |  | 4 | 7/13 | 8/3 | — | bar: Jul '26 7/13
Platform | Team Platform | Aurora service metrics (Gateway/Auth/Quota), tenant-attributed dashboards, metering pipeline lag metric | M2 | RACKAI-350 | Abhimanyu Sharma | In Progress |  | 3 | 2026-08-03 | 2026-08-21 | Platform M1 | bar: Aug '26 8/3
Platform | Team Platform | Loki log aggregation, structured log fields (tenant/project/service), AlertManager e2e validation | M3 | RACKAI-431 | Abhimanyu Sharma | In Progress |  | 6 | 2026-08-24 | 9/28 | Platform M2 | bar: Aug '26 8/24
Platform | Team Platform | VictoriaMetrics remote-write, 13-month retention, FineTuningJob Controller metrics | M4 | RACKAI-432 | Abhimanyu Sharma | In Progress |  | 3 | 10/5 | 10/19 | Platform M3 | bar: Oct '26 10/5
Metering | Team Metering | Project CRD + usage_records schema + MeteringEvent queue; full pipeline w/ identity context, inference metering, FineTuningJob CRD | M1 | RACKAI-352 | Rohit Rajak | In Progress |  | 8 | 7/27 | 9/14 | IAC M1 (identity) | bar: Jul '26 7/27
Metering | Team Metering | UsageSummary + UsageRecord APIs, historical usage, usage:view enforcement, FineTuningJob metering | M2 |  |  | Not Started |  | 2 | 9/14 | 9/21 | Metering M1, IAC M2 | bar: Sep '26 9/14
Metering | Team Metering | QuotaPolicy CRD, soft quota alerts | M3 |  |  | Not Started |  | 4 | 9/28 | 10/19 | Metering M2 | bar: Sep '26 9/28
Metering | Team Metering | Quota Enforcement Service, Redis counters, pre-execution admission control (429/402) | M4 |  |  | Not Started |  | 1 | 10/26 | 10/26 | Metering M3 | bar: Oct '26 10/26
Auditing | Team Audit/Obs | Audit Service core (Redis Streams, PostgreSQL audit-001), audit-003 CRD fields, request_id; K8s admission webhook, proposed-actor flow, FineTuningJob audit events | M1 |  |  | Not Started |  | 7 | 8/17 | 9/28 | IAC M1 (soft), Gateway request_id | bar: Aug '26 8/17
Auditing | Team Audit/Obs | audit-002 migration, audit-004 deletion fields, Pattern A controllers, quota/dataset/config audit logs, deletion events, finalizers | M2 |  |  | Not Started |  | 2 | 10/5 | 10/12 | Audit M1; Pattern A (IAC+Metering) | bar: Oct '26 10/5
Auditing | Team Audit/Obs | Billing audit, compliance validation | M3 |  |  | Not Started |  | 3 | 10/19 | 11/2 | Audit M2 | bar: Oct '26 10/19
Observability | Team Audit/Obs | Metrics API (inference latency/rate/errors, quota utilization), Workload Status API | M1 |  |  | Not Started |  | 3 | 9/14 | 9/28 | IAC M2 + Platform M1 ⭐ crit-path | bar: Sep '26 9/14
Observability | Team Audit/Obs | Logs API (Loki proxy), Alert Rule CRUD, 60s evaluation loop, webhook delivery | M2 |  |  | Not Started |  | 5 | 10/5 | 11/2 | Obs M1, Platform M3 | bar: Oct '26 10/5
Maintenance | Product | Ongoing product maintenance & support across the release window | — |  |  | Not Started |  | 35 | 6/29 | 2/22 | Continuous (from 6/29) | Jun '26 6/29: 35
RACKAI M2 FEATURES — product feature delivery (from 'RackAI M2' roadmap, anchored to July)
M2 Feature | S4–S5 | Inference routing |  | RACKAI-311 | Neelava Chatterjee | In Progress | 1 | 4 | 2026-07-13 | 2026-08-09 | IAC M1 (Gateway auth) | Jul '26 7/13: 4
M2 Feature | S4 | AMD+NVIDIA node support |  | RACKAI-263 | Rajendra Gosavi | Not Started | 1
M2 Feature | S4 | API Layer Validation |  | RACKAI-261 | Ajay Bedre | Complete | 1 | 1 | 2026-08-03 | 2026-08-09 | IAC M1 (auth) | bar: Aug '26 8/3
M2 Feature | S4 | CODB: Upgrade KServe and friends |  | RACKAI-258 | Neelava Chatterjee | Complete | 1 | 1 | 2026-08-03 | 2026-08-09 | bar: Aug '26 8/3
M2 Feature | S4 | CODB: Model parameter / recipe enhancements |  | RACKAI-269 | Unassigned | Not Started | 1
M2 Feature | S4 | CODB: Fix FT to be context parallel |  | RACKAI-340 | Rajendra Gosavi | Complete | 1 | 3 | 2026-06-30 | 2026-07-15 |  | Jun '26 6/29: 3
M2 Feature | S5 | Accelerator selection phase 3 |  | RACKAI-336 | Kim Nguy | Complete | 1 | 2 | 2026-10-26 | 2026-11-08 | Metering M4 | Oct '26 10/26: 2
M2 Feature | S5–S8 | AMD AIM engine integration |  | RACKAI-347 | Neelava Chatterjee | In Progress | 2
M2 Feature | S6 | Speculative Decoding |  | RACKAI-67 | Alberto Ferrer | In Progress | 3
M2 Feature | S6–S7 | DPO fine tuning |  | RACKAI-252 | Deshna Shah | In Progress | 3 | 4 | 2026-08-03 | 2026-08-30 |  | Aug '26 8/3: 4
M2 Feature | S7 | SLM support |  | RACKAI-360 | Unassigned | Not Started | 4
M2 Feature | S8 | Refrag |  | RACKAI-374 | Unassigned | In Progress | 4
M2 Feature | S8–S9 | Dataset Management Improvement |  | RACKAI-385 | Unassigned | In Progress | 4
M2 Feature | S9–S10 | Synthetic Data Generation |  | RACKAI-380 | Unassigned | In Progress | 5
M2 Feature | S9–S10 | AI Performance Benchmarks (Internal Benchmarking Process) |  |  |  | Not Started | 5
M2 Feature | TBD | GPU node access support |  |  |  | Not Started | 6 |  |  |  | Unscheduled – backlog
M2 Feature | TBD | Multi region support |  |  |  | Not Started | 6 |  |  |  | Unscheduled – backlog
M2 Maintenance | TBD | openCenter Upgrade (Dev) |  | RACKAI-357 | Dan Hand | Not Started |  | 1 | 2026-08-10 | 2026-08-14
M2 Maintenance | TBD | openCenter Upgrade (Staging) |  | RACKAI-358 | Unassigned | Not Started |  | 1 | 2026-08-24 | 2026-08-30 | bar: Aug '26 8/24
M2 Maintenance | TBD | Deploy Prod RackAI Prod) |  | RACKAI-359 | Unassigned | Not Started |  | 1 | 2026-08-31 | 2026-09-06 | bar: Aug '26 8/31
M2 Maintenance | TBD | End-to-end Deployment Automation (Infra, openCenter [K8s], RackAI, and BAIC) |  | RACKAI-224 | Dan Hand | In Progress
M2 Feature | TBD | Request new model support |  | RACKAI-354 | Ajay Bedre | In Progress |  | 2 | 2026-09-07 | 2026-09-20 |  | Sep '26 9/7: 2
M2 Feature | TBD | Fine Tuning - Checkpointing + resume |  | RACKAI-379 | Alberto Ferrer | Not Started
M2 Feature | TBD | Model Perfomance Benchmarking in RackAI |  | RACKAI-382 | Unassigned | In Progress
M2 Maintenance | TBD | Model Performance Troubleshooting |  |  |  | Not Started
M2 Maintenance | TBD | Workload Profiles UX |  |  |  | Not Started
M2 Feature | TBD | Sunsetting a model in RackAI |  | RACKAI-372 |  | Not Started
LEGEND
| IAC |  | Platform |  |  |  |  | Metering |  | Auditing |  | Jun '26 6/1: Observability; Jun '26 6/15: Maintenance; Jun '26 6/29: M2 Feature
⭐ = critical-path point · medium vertical rule = month boundary · dates = week-start (Mon) · Pri colour 1=red → 6=grey · 'mw' = man-weeks
Note on G7: Source: Jira RACKAI-204, https://rackspace.atlassian.net/browse/RACKAI-204. Jira status: "Closed" (Done category). Synced 2026-08-21. Updated from "In Progress".
Note on K7: Jovan Rajapakse: Jira RACKAI-204 has no Start date or Due date set — this is the project-plan schedule, not a Jira value. Checked 2026-08-04.
Note on G8: Source: Jira RACKAI-333, https://rackspace.atlassian.net/browse/RACKAI-333. Jira status: "Closed" (Done category). Synced 2026-08-21. Updated from "In Progress".
Note on K8: Jovan Rajapakse: Jira RACKAI-333 has no Start date or Due date set — this is the project-plan schedule, not a Jira value. Checked 2026-08-04.
Note on G9: Source: Jira RACKAI-351, https://rackspace.atlassian.net/browse/RACKAI-351. Jira status: "Closed" (Done category). Synced 2026-08-21. Matches sheet.
Note on K9: Jovan Rajapakse: Jira RACKAI-351 has no Start date or Due date set — this is the project-plan schedule, not a Jira value. Checked 2026-08-04.
Note on G11: Source: Jira RACKAI-353, https://rackspace.atlassian.net/browse/RACKAI-353. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Matches sheet.
Note on K11: Jovan Rajapakse: Jira RACKAI-353 has no Start date or Due date set — this is the project-plan schedule, not a Jira value. Checked 2026-08-04.
Note on G12: Source: Jira RACKAI-350, https://rackspace.atlassian.net/browse/RACKAI-350. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Matches sheet.
Note on K12: Jovan Rajapakse: Jira RACKAI-350 has no Start date or Due date set — this is the project-plan schedule, not a Jira value. Checked 2026-08-04.
Note on G13: Jovan Rajapakse: Source: Jira RACKAI-431, https://rackspace.atlassian.net/browse/RACKAI-431. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Updated from "Not Started".
Note on G14: Jovan Rajapakse: Source: Jira RACKAI-432, https://rackspace.atlassian.net/browse/RACKAI-432. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Updated from "Not Started".
Note on G15: Source: Jira RACKAI-352, https://rackspace.atlassian.net/browse/RACKAI-352. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Matches sheet.
Note on K15: Jovan Rajapakse: Jira RACKAI-352 has no Start date or Due date set — this is the project-plan schedule, not a Jira value. Checked 2026-08-04.
Note on G26: Jovan Rajapakse: Source: Jira RACKAI-311, https://rackspace.atlassian.net/browse/RACKAI-311. Jira status: "In Progress" (In Progress category). Synced 2026-08-21. Matches sheet.
Note on F27: Jovan Rajapakse: Source: Jira RACKAI-263, https://rackspace.atlassian.net/browse/RACKAI-263. Assignee synced 2026-08-21. Updated from "Unassigned".
Note on G27: Source: Jira RACKAI-263, https://rackspace.atlassian.net/browse/RACKAI-263. Jira status: "New" (To Do category). Synced 2026-08-21. Corrected from "In Progress" (prior sync mis-mapped this issue's status).
Note on G28: Jovan Rajapakse: Source: Jira RACKAI-261, https://rackspace.atlassian.net/browse/RACKAI-261. Jira status: "Closed" (Done category). Synced 2026-08-21. Updated from "In Progress".
Note on G29: Source: Jira RACKAI-258, https://rackspace.atlassian.net/browse/RACKAI-258. Jira status: "Closed" (Done category). Synced 2026-08-21. Updated from "In Progress".
Note on G30: Jovan Rajapakse: Source: Jira RACKAI-269, https://rackspace.atlassian.net/browse/RACKAI-269. Jira status: "New" (To Do category). Synced 2026-08-21. Updated from "In Progress".
Note on G31: Source: Jira RACKAI-340, https://rackspace.atlassian.net/browse/RACKAI-340. Jira status: "Closed" (Done category). Synced 2026-08-21. Updated from "In Progress".
Note on G32: Jovan Rajapakse: Source: Jira RACKAI-336, https://rackspace.atlassian.net/browse/RACKAI-336. Jira status: "Closed" (Done category). Synced 2026-08-21. Updated from "Not Started".
Note on F33: Jovan Rajapakse: Source: Jira RACKAI-347, https://rackspace.atlassian.net/browse/RACKAI-347. Assignee synced 2026-08-21. Updated from "Unassigned".
Note on G33: Jovan Rajapakse: Source: Jira RACKAI-347, https://rackspace.atlassian.net/browse/RACKAI-347. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Updated from "Not Started".
Note on G34: Jovan Rajapakse: Source: Jira RACKAI-67, https://rackspace.atlassian.net/browse/RACKAI-67. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Updated from "Not Started".
Note on G35: Jovan Rajapakse: Source: Jira RACKAI-252, https://rackspace.atlassian.net/browse/RACKAI-252. Jira status: "In Progress" (In Progress category). Synced 2026-08-21. Updated from "Not Started".
Note on G36: Jovan Rajapakse: Source: Jira RACKAI-360, https://rackspace.atlassian.net/browse/RACKAI-360. Jira status: "New" (To Do category). Synced 2026-08-21. Matches sheet.
Note on G37: Jovan Rajapakse: Source: Jira RACKAI-374, https://rackspace.atlassian.net/browse/RACKAI-374. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Updated from "Not Started".
Note on G38: Jovan Rajapakse: Source: Jira RACKAI-385, https://rackspace.atlassian.net/browse/RACKAI-385. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Updated from "Not Started".
Note on G39: Jovan Rajapakse: Source: Jira RACKAI-380, https://rackspace.atlassian.net/browse/RACKAI-380. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Updated from "Not Started".
Note on G43: Jovan Rajapakse: Source: Jira RACKAI-357, https://rackspace.atlassian.net/browse/RACKAI-357. Jira status: "New" (To Do category). Synced 2026-08-21. Updated from "In Progress".
Note on G44: Jovan Rajapakse: Source: Jira RACKAI-358, https://rackspace.atlassian.net/browse/RACKAI-358. Jira status: "New" (To Do category). Synced 2026-08-21. Matches sheet.
Note on G45: Jovan Rajapakse: Source: Jira RACKAI-359, https://rackspace.atlassian.net/browse/RACKAI-359. Jira status: "New" (To Do category). Synced 2026-08-21. Matches sheet.
Note on G46: Source: Jira RACKAI-224, https://rackspace.atlassian.net/browse/RACKAI-224. Jira status: "In Progress" (In Progress category). Synced 2026-08-21. Matches sheet.
Note on K46: Jovan Rajapakse: Jira RACKAI-224 has no Start date or Due date set — this is the project-plan schedule, not a Jira value. Checked 2026-08-04.
Note on F47: Jovan Rajapakse: Source: Jira RACKAI-354, https://rackspace.atlassian.net/browse/RACKAI-354. Assignee synced 2026-08-21. Updated from "Unassigned".
Note on G47: Jovan Rajapakse: Source: Jira RACKAI-354, https://rackspace.atlassian.net/browse/RACKAI-354. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Updated from "Not Started".
Note on G48: Jovan Rajapakse: Source: Jira RACKAI-379, https://rackspace.atlassian.net/browse/RACKAI-379. Jira status: "New" (To Do category). Synced 2026-08-21. Matches sheet.
Note on G49: Jovan Rajapakse: Source: Jira RACKAI-382, https://rackspace.atlassian.net/browse/RACKAI-382. Jira status: "In Analysis" (In Progress category). Synced 2026-08-21. Updated from "Not Started".

## RackAI M2 (hidden)
[11 empty] | July | Aug | Aug | Sep | Sep | Oct | Oct | Nov
Feature | Task | Man weeks | Priority | Start Date | End Date | Status | Owner | Requirements Doc | Tech Spec | Jira | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint Total man weeks | Requirements Doc
Inference routing |  | 4 | 1 | [6 empty] | https://rackspace.atlassian.net/browse/RACKAI-311 | July: 2; Aug: 2 | 4
Add llm-d to RackAI
Routing from ingress to llm-d to model
Add shared KV cache
AMD AIM engine integration |  | 8 | 2 | [6 empty] | https://rackspace.atlassian.net/browse/RACKAI-347 | Aug: 2; Aug: 2; Sep: 2; Sep: 2 | 8
Design RackAI integration with AIM engine
Accelerator selection phase 3 |  | 2 | 1 |  |  |  |  | Accelerator_Selection_TechSpec.docx | Accelerator_Selection_TechSpec.docx | https://rackspace.atlassian.net/browse/RACKAI-188, https://rackspace.atlassian.net/browse/RACKAI-336 | Aug: 2 | 2
Build/Maintain inventory of nodes
GPU consumption metrics
SLM support |  | 2 | 4 | [7 empty] | Sep: 2 | 2
Add SLM relevant to Uniphore to the model catalog
GPU node access support |  |  | 6
AMD+NVIDIA node support |  | 2 | 1 |  |  |  |  | RACKAI-AMD-PRD.docx |  | https://rackspace.atlassian.net/browse/RACKAI-263 | July: 2 | 2
Inference deployment on compatible GPU node
Fine tuning job on compatible GPU node
DPO fine tuning |  | 4 | 3 |  |  |  |  | RACKAI-AMD-PRD.docx |  | https://rackspace.atlassian.net/browse/RACKAI-252 | Aug: 2; Sep: 2 | 4
Synthetic Data Generation |  | 4 | 5 | [5 empty] | RXT_SyntheticDataPlatform_TechSpec_v0.1.docx |  | Oct: 2; Oct: 2 | 4
AI Performance Benchmarks |  | 4 | 5 | [5 empty] | rackspace-aiperf-tech_spec.docx |  | Oct: 2; Oct: 2 | 4
Speculative Decoding |  | 2 | 3 | [7 empty] | Aug: 2 | 2
Refrag |  | 2 | 4 | [7 empty] | Sep: 2 | 2
Dataset Management Improvement |  | 4 | 4 | [7 empty] | Sep: 2; Oct: 2 | 4
Download data from URL
Multi region support |  |  | 6 | [15 empty] | 0
Observability for RackAI user |  | 4 | 2 | [15 empty] | 4 | bar: Aug to Sep
API Layer Validation | Introduce API layer validation for data objects in RackAI | 1 | 1 | [6 empty] | https://rackspace.atlassian.net/browse/RACKAI-261 | [8 empty] | 1 | bar: July
CODB: Upgrade KServe and friends | Upgrade and migrate existing components | 2 | 1 | [6 empty] | https://rackspace.atlassian.net/browse/RACKAI-258 | July: 2 | 2
CODB: Model parameter/recipe enhancements | Fix all model parameters and ensure they are being deployed with optimal configuration | 1 | 1 | [6 empty] | https://rackspace.atlassian.net/browse/RACKAI-269 | [8 empty] | 1 | bar: July
Product Maintenance | Fix FT to be context parallel | 4 | 1 | [7 empty] | Aug: 2; Aug: 2 | 4
| Total man weeks | 50 | [8 empty] | 8 | 9 | 9 | 7 | 7 | 6 | 4 | 0 | 50
Priority | Feature
1 | Accelerator selection phase 3
AMD+NVIDIA node support
API Layer Validation
CODB: Model parameter/recipe enhancements
CODB: Upgrade KServe and friends
Inference routing
2 | AMD AIM engine integration
Observability for RackAI user
3 | DPO fine tuning
Speculative Decoding
4 | Dataset Management Improvement
Refrag
SLM support
5 | AI Performance Benchmarks
Synthetic Data Generation
6 | GPU node access support
Multi region support

## Future ideas requirements (hidden)
Token accounting?
Configuration toggles implemented to select NIM vs. vLLM at deployment time.

## Action Tracker (hidden)
Item | Owner | Status | Notes
Produce BGV Reports for P9'ers | Paavan | In Progress
Setup Jira board | Paavan | Not Started
Setup GitHub Mirroring | Erik | Not Started
Publish Tech Spec | Alberto | Not Started | Tech Spec - https://raxglobal.sharepoint.com/:w:/r/sites/PVCEngineering/Shared%20Documents/Project%20Kickoffs%20-%20Specs%20-%20Estimation/PVC%20-%20RackAI/Product%20Tech%20Spec%20-%20RackAI%20(Uniphore)%20-%20LA.docx?d=w023598787b1b43f0a5b968f9640711d2&csf=1&web=1&e=fBgv2Y PRD - https://raxglobal.sharepoint.com/:w:/r/sites/PVCEngineering/Shared%20Documents/Project%20Kickoffs%20-%20Specs%20-%20Estimation/PVC%20-%20RackAI/PRD%20-%20RackAI%20(Uniphore)%20-%20LA.docx?d=w2b90344a789b4c14a86aa3a2a1312a4f&csf=1&web=1&e=VWpCmg
Setup Twice-Weekly Stand-Ups | Jovan | Not Started
Setup MS Teams Channel | Jovan | Not Started

## Questions to Uniphore (hidden)
Feature Group | S. No. | Question for Clarification | Priority | Answer | Comments
API Parity | 1 | Are OpenAI-compatible APIs the only ones being considered from an inference perspective? |  |  | Paavan: Yes, only OpenAI APIs are relevant per the PRD shared recently
API Parity | 2 | Is Anthropic Compatible API a requirement? |  |  | Paavan: No. See above
API Parity | 3 | RMPAI currently lacks a responses API for built-in custom tool calling (MCP integration). Is this a requirement?
API Parity | 4 | How important is the auto-scaling feature? What specific scenarios, if any, are being considered for auto-scaling (e.g., predictable traffic, performance optimization, or cost reduction provided by Fireworks AI)? |  |  | Paavan: Currrently out of scope of phase 1?
API Parity | 5 | Is using Hugging Face as the sole model registry sufficient? |  |  | Paavan: There has been an ask for private registry. Priority is being determined
API Parity | 6 | Do we need to host a private model registry to support custom model uploads, or is Hugging Face sufficient for hosting private models? |  |  | Paavan: There has been an ask for private registry. Priority is being determined
API Parity | 7 | In fine tuning, between SFT, RFT and DPO which ones are key? Which APIs are important to begin in the initial versions of the product? |  |  | Paavan: SFT first - likely with PEFT. Need to still get information regarding the APIs
API Parity | 8 | Is support for secret management via APIs required?
NVIDIA NIM Support | 9 | Any specific NVIDIA hardware specs do we need to support for NIM deployments?
NVIDIA NIM Support | 10 | Do we want to build using NIM ecosystem? Or just use NIM models? |  |  | Paavan: Only NIM models
Fine-Tuning | 11 | What fine-tuning algorithms (e.g., LoRA, QLoRA, full parameter) are mandatory for the initial release? |  |  | Paavan: SFT and PEFT. Let's start with LORA, QLORA
Fine-Tuning | 12 | Do we need to even expose underline details like LoRA, QLoRA to customers ? Usually platforms like Azure AI Foundry, AWS Bedrock or Fireworks AI they do not expose such details. What all types of Fine tunning methods we are offering from this list - [ Supervised Fine Tuning (SFT) , Reinforcement Learning (RL) , Direct preference optimization (DPO) ] |  |  | Paavan: SFT and LORA adapter is the first milestone focus.
Fine-Tuning | 13 | How our system is supposed to accept input for fine tuning job ( Sample data & Validation data) ? Are we supporitng file uploads or cloud storage options like S3/blobstore in this case? |  |  | Paavan: Data comes as a file upload to the API. Where it is stored should be decided by the product internally.
Fine-Tuning | 14 | What all hyperparameters we are looking to expose to the users while configuring the FT job ? Any prior expectations from Uniphore/Racksapce here |  |  | Paavan: See the doc shared by Rackspace
Fine-Tuning | 15 | Post FT job artifacts - any requirements on where and how they are stored? |  |  | Paavan: Should go in a model registry. Likely local and not HF.
Misc | 16 | Are we going with the single cluster deployment for RMPAI? And is it single region/AZ? |  |  | Paavan: Single Cluster for now.
Misc | 17 | Are there any automation requirements? API, CLI, tool integration like terraform? |  |  | Paavan: API and CLI support is a must for all features going out now.

## Questions to RXT (hidden)
Questions
Delivery Platform - SNOW?
Billing?
Authentication